## Sheet1
Sprint 3
| Req. # | Description | Story Points | Name
| 1 | Create a landing page that introduces the app and provides navigation to key features like lot availability and stats | 8
Merged | 5 | Provide a calendar view showing dates and times when parking is restricted due to campus events(e.g. Basektball Game) | 8
PR Made | 6 | Allow users to submit bug reports or feedback directly to the app administrators. | 5 | Tanu
| 7 | Provide a toggle for users to switch between dark and light UI themes. | 5 | Kaden
PR Made | 9 | Display a banner notification on the homepage (e.g., “Restricted parking today!”) during special events. | 5 | Sriya
| 12 | Add a tab asking users to rate their experience or suggest improvements | 5 | Tanu
Merged | 13 | Ensure color-blind accessibility and readable text contrast for all UI elements | 1 | Anna
Merged | hot fix | Update refresh button (find a new spot for it) | 1 | Anna
| hot fix | Resolve searching issue | 1 | Kaden
| hot fix | Fix Timing to make them all the same | 1 | Sabeen