## Sheet1
Sprint
Completed | Req. # | Description | Story Points | Name
| 15 | Add a filter that filters based on availability, permit, and distance | 3 | Anna
| 10 | Allow users to search for a specific parking lot by name or permit type within the app. | 5 | Kaden
| 8.1 | Add a manual refresh button to allow users to reload parking availability data. | 3 | Sriya
| 8.2 | Display the last updated time for parking data to inform users of data freshness. | 1 | Sabeen
| 2.1 | Implement a statistics page that shows data on parking lot usage trends, including peak and off-peak hours | 8 | Samantha
| 2.2 | Display busy hours on the stats page using color coding (e.g., green for light, yellow for moderate, red for heavy usage) | 3 | Tanu
| 11 | App saves previous filters used for parking lot searching | 4 | Anna
Backlog
| Req. # | Description | Story Points | Priority | Sprint Number
| 1 | Create a landing page that introduces the app and provides navigation to key features like lot availability and stats | 8 | High
| 2.1 | Implement a statistics page that shows data on parking lot usage trends, including peak and off-peak hours | 8 | High | 2
| 2.2 | Display busy hours on the stats page using color coding (e.g., green for light, yellow for moderate, red for heavy usage) | 3 | Medium | 2
| 3.1 | Display the total number of available and occupied parking spots for each lot across campus. | 2 | High | 1
| 3.2 | Use a progress bar visualization to indicate how full each parking lot is in real time. | 3 | Low | 2
| 4.1 | Mark parking lots available to yellow permit holders. | 2 | Medium | 1
| 4.2 | Mark parking lots available to red permit holders. | 2 | Medium | 1
| 4.3 | Mark parking lots available to Central District Parking Garage Holders | 2 | Medium | 1
| 4.4 | Mark parking lots available to Union Garage holders. | 2 | Medium | 1
| 5 | Provide a calendar view showing dates and times when parking is restricted due to campus events(e.g. Basektball Game) | 8 | Low
| 6 | Allow users to submit bug reports or feedback directly to the app administrators. | 5 | Low
| 7 | Provide a toggle for users to switch between dark and light UI themes. | 5 | Low
| 8.1 | Add a manual refresh button to allow users to reload parking availability data. | 3 | High | 2
| 8.2 | Display the last updated time for parking data to inform users of data freshness. | 1 | Medium | 2
| 9 | Display a banner notification on the homepage (e.g., “Restricted parking today!”) during special events. | 3 | Low
| 10 | Allow users to search for a specific parking lot by name or permit type within the app. | 5 | Medium | 2
| 11 | App saves previous filters used for parking lot searching | 4 | low | 2
| 12 | Add a tab asking users to rate their experience or suggest improvements | 2 | Low
| 13 | Ensure color-blind accessibility and readable text contrast for all UI elements | 1 | Low
| 14 | A map that displays where the parking lot is located | 5 | Medium | 1
| 15 | Add a filter that filters based on availability, permit, and distance | 3 | High | 2